| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1a): Assure that the health program is governed by an extensive set of school board-approved policies that are consistent with best practice recommendations of state and federal agencies or professional education and health organizations. (As appropriate, multiple, separate policies should be in place for each of the 11 CSHP Characteristics.) |
| Priority time (check): Short Term ______ Long Term _X_____ | Priority level (check): High _______ Medium _________ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| School Board Policy acknowledges and has developed policy in conjunction with CSHP characteristics | Board Policy | School Board Members | Spring 2010 | Online School Board Manual |
| Administrative Guidelines will be developed to implement School Board Policy | Board Policy Administrative Guidelines | Superintendent Administrators | Spring 2010 | Administrative Guidelines Manual |

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1b): Assure that all health program staff members, including health education and physical education teachers, are properly credentialed and well qualified. |
| Priority time (check): Short Term ______ Long Term __X____ | Priority level (check): High ___X____ Medium _________ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| All Secondary Health and Physical Education teachers are licensed in accordance to state guidelines | Applitrack Principals Professional Standards Board | Principals | Ongoing with hiring process | Certified Teachers |
| All Health Care Personnel are certified | Applitrack Professional Standards Board | Central Office and Head Nurse | Ongoing | Certified Nursing Staff |

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1c): On a regularly scheduled basis, require all appropriate staff members to attend professional development activities related to implementation of health program policy in their area(s) of responsibility.. |
| Priority time (check): Short Term ____X__ Long Term ___X___ | Priority level (check): High ____X___ Medium _________ Low _____ |
| Determine short-term and long-term professional development goals. | CSHAC Steering Committee Meetings | CSHAC Steering Committee | October 2009 | Short-term and Long-term professional goals. |
| Determine resources for short-term professional goals for immediate implementation. | Community Partners, School Staff | CSHAC Committee | October 2009 | Professional Development Catalog |
| Determine resources for long-term professional development goals. | Community Partners, School Staff | CSHAC Committee | Ongoing | Professional Development Catalog |
| Provide opportunities for school staff to become trainers in health and wellness programs. | Conferences, Workshops, Webinars, Book Studies | CSHAC Committee | Ongoing | Professional Development Catalog |
| The Professional Development Catalog will include opportunities to extend and learn methods for incorporating health and wellness. | District Web Site, Webinars | Central Office Staff & CSHAC Steering Committee | Annually in the fall | Attendance of staff |
| Equipment Training for staff in cardio room at Hobart Middle School |  |  | Ongoing |  |

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1d): Provide all staff members the time and resources required to comply with health program policies. |
| Priority time (check): Short Term ______ Long Term ______ | Priority level (check): High _______ Medium _________ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| Professional Development Opportunities will be provided before, during and after school. | Professional Development Catalog | CSHAC Steering Committee and Central Office | Ongoing | Attendance Logs |

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1e): Require administrators and supervisors to attend professional development that prepares them to authoritatively monitor health policy compliance. |
| Priority time (check): Short Term ______ Long Term __X____ | Priority level (check): High _______ Medium ___X______ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| A monitoring tool will be developed for use by administrators to assess health policy compliance. | State and Federal Guidelines and School Board Policy, | CSHAC Steering Committee | Fall 2010 | Health Policy Compliance Tool |

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.1f): Assure that administrators and supervisors routinely monitor compliance with all health policies and take action to remedy deficiencies. |
| Priority time (check): Short Term ______ Long Term _X_____ | Priority level (check): High _______ Medium ___X______ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| Administrators analyze strengths and weaknesses of health policies to develop a plan of action. | Health Policy Compliance Tool | Principals, CSHAC Steering Committee | Annually in Spring 2010 | Healthy Policy School Reports |

HEALTHY SCHOOL IMPROVEMENT PLAN FORM

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.2a): Periodically develop strategic plans for all aspects of the health program, including coordination. |
| Priority time (check): Short Term ______ Long Term ___X___ | Priority level (check): High _____X__ Medium _________ Low ________ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| CSHAC Committee will meet annually to review Health and Wellness Plan – | Health and Wellness Plan, Attendance Logs from Prof. Dev. Catalog, Health Policy Compliance School Reports, Student Health Data and Survey Data | CSHAC Committee and Principals, PE Teachers | Annually in May | Data Profile |
| School Health Goal Teams are created at the district for the schools with input from stake holders. | Health and Wellness Plan | NCA Goal Team | March 2010 | Goal Plan as it relates to Health and Wellness Plan. |

HEALTHY SCHOOL IMPROVEMENT PLAN FORM

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.2b): Collect confidential student health indicator data at least once every two years and carefully consider when determining strategic plan objectives and activities. |
| Priority time (check): Short Term ______ Long Term _X_____ | Priority level (check): High _______ Medium ____X_____ Low ________ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| Baseline data will be collected from Hobart Middle School using the Fitness Gram test. National Norm charts will be shared. |  |  |  |  |
| Physical fitness testing data will be collected from Hobart High School student, National Norm charts will be shared. |  |  |  |  |
| Physicalfitness results will be shared with CSHAC committee |  |  |  |  |

HEALTHY SCHOOL IMPROVEMENT PLAN FORM

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.2c): Use results of periodic health program needs and status assessments in the strategic planning process. |
| Priority time (check): Short Term ______ Long Term ___X___ | Priority level (check): High _______ Medium ___X______ Low ________ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| Analyze data collected from monitoring assessments to determine needs | Monitoring Assessments | CSHAC | Annually | Meeting notes |

HEALTHY SCHOOL IMPROVEMENT PLAN FORM

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.2d): On a regular basis, monitor progress toward fully implementing the health program strategic plan. |
| Priority time (check): Short Term ______ Long Term _X_____ | Priority level (check): High ___X____ Medium _________ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| CSHAC committee hears data reports at their annual spring meeting. | Healthy Policy Compliance School Report, Attendance Logs from professional Development, Student Data | CSHAC Committee | Annually in May | Data Profile updated and reported |
| Based on the data profile reported the CSHAC will conduct a report card of annual progress. | District Health Plan Report Card | CSHAC Committee | Annually in May | District Health Plan Report Card |

HEALTHY SCHOOL IMPROVEMENT PLAN FORM

| Characteristic I: School Health Program Policy and Strategic Planning |
| --- |
| Objective (1.2e): Identify and report benefits of the school health program to participants, the school, and the school district. |
| Priority time (check): Short Term ______ Long Term ___X___ | Priority level (check): High __X_____ Medium _______ Low _____ |
| Activities | Resources | Individual or Group Responsible | Completion Date | Evidence of Completion |
| After Annual Meeting of CSHAC activities are featured on schoolwires, in community and school newsletters | Minutes from meeting | CSHAC | One Month after Annual Meeting | Website Postings and copies of Newsletters |